## Work Plan
Meetings | TASKS Groups | 2021-06-04 | 2021-06-11 | 2021-07-02 | 2021-07-09 | 2021-07-16 | 2021-07-23
Task Group Work | Policy and Program Inventory |  | Present products of Tasks 1 + 2 | Present Task 4 | Present drafts of Task 3
|  |  | Solicit feedback from SC | Solicit feedback from SC | Solicit feedback from SC
|  |  | Refine inventory based on feedback | Refine threat and hazard list based on feedback | Refine draft recommendations
| CAP Recommendations |  | Come to consensus on definition for Critical Infrastructure | Present drafts on Tasks 2 + 3 | Present drafts on Tasks 4 + 5 | Present drafts on Task 1 | Discuss and refine draft recommendations Tasks 1, 2, 3, 4, 5
|  |  | Engage with Cross-Sector SC for Task 1 as needed | Evaluate and solicit feedback from SC | Evaluate and solicit feedback from SC | Evaluate and solicit feedback from SC
| Municipal Vulnerability | Revisit GMP and ANR Tools
Subcommittee Meetings | Present | - Revised summer work plan for sub-committee - CAP Input Template - Revisit GMP MVI Tool | Draft Inventory Tasks 1+2 | Inventory Task 4 Recommendations Tasks 2+3 | Inventory Task 3 Recommendations Tasks 4 + 5 | Recommendations Task 1
| Plan | Refine work plan and milestones
| Deliberate | Municipal Capacity Measures (MVI) Revisit GMP and ANR Tools | - Deliberate presented Task drafts - CI Definition | Deliberate presented Task drafts | Deliberate presented Task drafts | Deliberate presented Task drafts | Review all recommendations together, refine, identify any points of contention. Begin to put in VCC template.
| Decide | Agreement on Work Plan Decide on MVI Tool | - Consensus on CI definitiion - Finalize detailed summer work plan | Finalize Inventory Tasks 1 + 2 | - Finalize Inventory Task 4 - Finalize CAP Recommendations 2 + 3 | - Finalize Inventory Task 3 Finalize CAP Tasks 4+5 | Decide what slate of draft recommendations to forward to VCC for public engagement

## Task Groups
Task Group | Objective | Participants | Tasks
Policy and Program Inventory TG | 1. Review existing planning efforts, including local and regional land use planning, transportation planning, energy planning and operations planning, | Joe Segale, Stephanie Smith, Marian Wolz, Mike Burke, Karen Horn, Anne Margolis | 1. Inventory and analysis of current plans, programs, policies. Review should assess whether item supports GHG reductions and whether inequities are specifically addressed. 2. Identify where gaps exist to better integrate items to support GHG emission reduction and building resilience. 3. Recommendations on policies, legislation, programs or operations to resolve identified gaps. 4. Develop list of threats and hazards and impact overall climate change resilience and rank in terms of impact and probability.
CAP Recommendations TG | 2. Develop best practice recommendations specific to rural communities for: reducing municipal, school district, and residential fossil fuel consumption; fortifying critical transportation, electricity, and community infrastructure; expanding the use of nature-based solutions to enhance landscape resilience in the built environment; and creating a distributed, redundant, storage-supported local electrical system. | 1- Ann Lawless, David Snedecker, Chad Farrell 2. Joe Segale 3. Mike Burke, Chad Farrell and Anne Margolis 4. Ben Rose, Marian Wolz, and Stephanie Smith 5. Jens Hilke, Ben Rose, Marian Wolz, and Stephanie Smith | 1.Refine cross sector mitigation recommendations on reducing GHG emissions for rural communities. 2. Develop recommendations for fortifying transportation infrastructure. 3. Develop recommendations for fortifying electrical and communications infrastructure and implementation of storage-support local electrical systems. 4. Develop recommendations for fortifying other critical community infrastructure. 5. Develop recommendations to expand the use of nature-based solutions to enhance landscape resilience in the built environment.
Municipal Vulnerability Index TG | Develop a “municipal vulnerability index” to identify those communities or parts of communities that may be most adversely affected by climate change. | Erica Bornemann, Catherine Dimitruk, Karen Horn, Stephanie Smith, Joe Segale, Mike Burke
Tool Development TG | Recommend accessible tools for municipalities to efficiently assess their climate emergency preparedness, consider land use changes that reduce vulnerabilities, evaluate their financial capacity to address infrastructure resilience, and prioritize investment in that infrastructure.
Vulnerable Populations TG | Recommend a means of securely sharing self-identified vulnerable residents’ information with State and local emergency responders and utilities; | VEM Staff | 1. Inventory methods used by other jurisdictions to inform the CARE program. 2. Develop recommendations for modifications to the CARE program including an outreach and educational strategy and funding needs.
Biennial Reporting | Utilize Vermont Emergency Management biennial reports to recommend program, policy, and legislative changes that will enhance municipal resilience to increased hazards presented by climate change. | VEM Staff | 1. VEM will assess Local Emergency Management Plans, Local Hazard Mitigation Plans and other relevant data to produce a biennial report on plan completion. Biennial reports will incorporate municipal vulnerability index data when available. 2. Sub-committee will review reports on an annual basis for implication on policy recommendations.