## Sheet1
Science and Data Summer Workplan
Meetings | TOPICS/TASKS | Completed | 2021-06-09 | 2021-06-16 | 2021-06-23 | 2021-06-30 | 2021-07-07 | 2021-07-14 | 2021-07-21 | 2021-07-27 | Aug-Sept
Integrated Issues Throughout |  | TEK/Equity/Co-Benefits | TEK/Equity/Co-Benefits | TEK/Equity/Co-Benefits | TEK/Equity/Co-Benefits | TEK/Equity/Co-Benefits | TEK/Equity/Co-Benefits | TEK/Equity/Co-Benefits | TEK/Equity/Co-Benefits | TEK/Equity/Co-Benefits
Full Subcmtee | Work Plan | Draft Workplan | 2021-06-09: Finalize detailed work plan; subject to future revisions
Task Leads | GHG Inventory | Discussion of difference b/w 10VSA 582 and SWSA requrements; Overview of tools and methods used in current inventory | 2021-06-09: Assign point person for consultant; Submit questions to be answered; 2021-06-16: Review Technical Consultant's survey of other jurisdiction's approaches; recommendation re adjustments to GHG inventory; 2021-06-23: Brief update from all Task Leads+F5; 2021-07-07: Finalize Draft Recommendations for VCC; prepare ppt | Consultant completes carbon buget report for 2 week review
| Carbon Budget |  | 2021-06-16: Agree to defiinitions of terms, e.g. gross, / net, biogenic CO2, land use change, carbon budget, etc.; Determine timeframe; Preliminary conversation with Cadmus re approach; 2021-06-23: Review preliminary carbon budget methodology by consultant; 2021-06-30: Cadmus finalizes carbon budget methodology and data recommendation
| LEAP Modeling | Presentation on LEAP modeling and timeline | 2021-06-09: LEAP Reference Case Review results and assumptions; 2021-07-07: Review results of Mitigation pathway- results and assumptions; identify other scenarios to be evalutated; 2021-07-14: Finalize Draft Recommendations VCC; prepare ppt | Review scenarios, results of final modeling
| Climate Data, Impacts, & Modeling |  |  | land use data for municipal vulnerability | Identify geographic and demographic emissions modeling gaps and data improvements (including LEAP) |  | Review results of VT Climate Impact Assessment; identify gaps for CAP overarching impacts narrative | Work with consultant to Identify sources for data addressing gaps; | Review consultant's recommendations; Prepare ppt for VCC
| Human /Health Impacts |  | 2021-06-09: Review Human Dimensions & Health Analysis; 2021-07-21: Finalize Draft Recommendations for VCC; prepare ppt
| Social Cost of Carbon | Decision to use currently available methodology; Develop questions tfor Consultant re SCC approaches; cost-benefit approaches |  | Get briefing on PSD Cost of Carbon study | Provide input to consultant on VT specific c/b, including social and environmental impacts; values from damage & abatement cost methodologies; discount rates; and sensitivity analyses | Review Consultant's summary and recommendations of SCC and c/b questions; submit recommendations to subcommittee re methodology, discount rate, demographic and intergenerational impacts | Determination of co-benefits? |  |  | Finalize Recommendation of how to value co-benefits and costs of GHG emissions reductions | Review results of Consultant's cost analyses
| Identification of Data Gaps; Develop Monitoring & Assessment Strategy |  | 2021-06-16: Identify data needs/ assumptions to improve in furture; 2021-07-27: Begin to develop or establish the process to devleop data governance protocols | Work with Consultant on development of data sources and reporting framework and protocols for tracking tool
Subcommittee Meetings | Present |  | SEI - LEAP BAU results; Cadmus - overall workplan and timeline; | Cadmus - initial GHG inventory findings; SCC approach |  | Cadmus - Cost of carbon & carbon budget recommendations; SEI - LEAP Mitigation Pathway results | Review results of VT Climate Impact Assessment & Human health Dimensions assessment; identify gaps for CAP overarching narrative | Cadmus - status report; | UVM Climate Impacts Assessment/Reslience Matrix | July 26 - Present to VCC;
| Plan | Create draft workplan | 2021-07-27: Develop detailed workplan for Aug/Sept
| Brief |  |  | Brief updates from all Task Leads; Brief on municipal vulnerability data needs and rural resilience from Resilence Subcmtee | Brief update from all Task Leads | Brief update from all Task Leads | Brief update from all Task Leads | LEAP modeling and Climate Data/Modeling present data gaps and sources to meet them
| Deliberate |  | Review LEAP BAU results and assumptions |  | Discuss SCC and GHG inventory initial findings and/or approach; Provide input to Cadmus; Discuss Just Transition Equity Principles and Screening tool application to S&D |  | Discuss integration of LEAP Pathway data and results with Subcmtee liaisons; |  | . | Debrief feedback from Council on S&D recommendations
| Decide |  | Finalize detailed work plan subject to future revisions; Assign Task Leads and supporting group members |  | Assign TL to develop summary for VCC presentation on S&D reccommendations | Approve or suggest modifications to Cadmus GHG inventory, Cost of Carbon, and carbon budget recs | Determine next steps for Climate impacts overview |  |  | Decide what topics to forward to VCC for public engagement